## Roadmap Tasks
Day | Date | Workstream | Task | Owner | Status | Est. Hours | Definition of Done
Day 1 | 2025-10-25 | Desktop/Electron | Repo + tooling + layout + theme | Owner | Not started | 2.5 | DoD: app boots; nav shell; toasts/dialogs
Day 1 | 2025-10-25 | Desktop/Electron | Login screen (mock auth + route guard) | Owner | Not started | 1 | DoD: mock login redirects to dashboard
Day 1 | 2025-10-25 | Menu | CSV upload UI + validation + preview (20 rows) | Owner | Not started | 2 | DoD: valid previews; invalid shows errors
Day 1 | 2025-10-25 | Menu | Manual create categories + items + sizes + veg flag | Owner | Not started | 1.5 | DoD: manual add/edit works; counts update
Day 1 | 2025-10-25 | Menu | Menu Summary (cards + counts + edit/delete/complete) | Owner | Not started | 1 | DoD: summary reflects changes
Day 1 | 2025-10-25 | Menu | Frequent Bought (UI select + reorder) | Owner | Not started | 0.75 | DoD: list renders and reorders visually
Day 2 | 2025-10-26 | POS | Create Order page (Frequent + Category→Items + Search) | Owner | Not started | 2.5 | DoD: assemble order in UI
Day 2 | 2025-10-26 | POS | Order Summary card (lines, Chef Tip, Type, Cancel/Place) | Owner | Not started | 1.5 | DoD: place creates draft (mock)
Day 2 | 2025-10-26 | Orders | Manage Orders (filters + detail + transitions UI) | Owner | Not started | 2 | DoD: allowed transitions enforced (UI)
Day 2 | 2025-10-26 | Dashboard | KPIs (Total/New/InKitchen/Ready) + sort/filter | Owner | Not started | 1 | DoD: counts update with state
Day 2 | 2025-10-26 | Settings | Template download + Delete All Data (mock) | Owner | Not started | 0.5 | DoD: delete clears mock store
Day 3 | 2025-10-27 | Android | Project + tabs (Chef: New/Preparing, Waiter: Ready) + mock login | Owner | Not started | 1.5 | DoD: skeleton navigates; role gating
Day 3 | 2025-10-27 | Android | Chef/New: Accept (Created→Accepted→auto InKitchen) | Owner | Not started | 1 | DoD: state moves correctly (mock)
Day 3 | 2025-10-27 | Android | Chef/Preparing: show items + Chef Tip; Mark Prepared | Owner | Not started | 1 | DoD: prepared updates Ready list (mock)
Day 3 | 2025-10-27 | Android | Waiter/Ready: Mark Delivered | Owner | Not started | 0.75 | DoD: delivered state set (mock)
Day 3 | 2025-10-27 | Android | Local notifications + sounds + mute toggle | Owner | Not started | 1 | DoD: notifications fire on state changes
Day 3 | 2025-10-27 | Android | Offline cache (JSON or Room), load on start | Owner | Not started | 1 | DoD: lists show when offline
Day 4 | 2025-10-28 | Backend | Firebase project setup + configs (web + android) | Owner | Not started | 0.75 | DoD: both apps init Firebase
Day 4 | 2025-10-28 | Backend | Auth integration (email/password) + seed users | Owner | Not started | 1 | DoD: real login works; role gating
Day 4 | 2025-10-28 | Backend | Firestore repositories (CRUD, queries, realtime) | Owner | Not started | 2 | DoD: both apps on Firestore
Day 4 | 2025-10-28 | Backend | Security rules (admin/chef/waiter) + sanity tests | Owner | Not started | 0.75 | DoD: rules deployed; negative tests pass
Day 4 | 2025-10-28 | Backend | Cloud Functions: orderNumber, onOrderStatusWrite, dangerDeleteAll | Owner | Not started | 1.5 | DoD: triggers fire; counter increments
Day 4 | 2025-10-28 | Backend | FCM topics + notification validation | Owner | Not started | 0.75 | DoD: devices receive pushes
Day 4 | 2025-10-28 | QA/Build | Full acceptance run + Electron build + signed APK + demo script | Owner | Not started | 1.5 | DoD: checklist green; artifacts ready

## Daily Summary
Day | Date | Planned Outcomes
Day 1 | 2025-10-25 | Electron UI skeleton, Menu flows, CSV validation complete; Frequent Bought UI
Day 2 | 2025-10-26 | POS + Manage Orders + Dashboard complete (UI); status rules enforced; Settings
Day 3 | 2025-10-27 | Android Chef/Waiter UI flows over mock; local notifications; offline cache
Day 4 | 2025-10-28 | Firebase wiring (Auth/Firestore/Functions/FCM); security rules; full QA + builds

## Risks
Risk | When | Symptom | Mitigation
CSV/Excel quirks | Day 1–2 | Validation slow/incorrect | Support CSV first; cap preview; error summary
FCM/device setup | Day 4 | Notifications not delivered | Use topics; test on one real device; fallback to Firestore listeners + local notifications
Firestore indexes | Day 2–4 | Index required errors | Accept prompts; keep queries simple (status + timestamps)
Security rules too strict | Day 4 | Writes blocked | Temporarily relax to auth-only for demo; tighten after
Functions cold starts | Day 4 | Delayed pushes | Keep functions minimal; single region; prewarm with test write